Lydiard Millicent Neighbourhood Plan

Minutes

Tuesday 3rd April 2018

Attendance: M Sharp (Chair), T Pepperall, M Groom, P Ruzzi,

Welcome to Andrew Collett, who agreed to join the Steering Group

Apologies: S Wheeler, P Cole, A Hutchinson

1. Healthcheck

The Healthcheck was discussed. Many comments and suggestions were included in the report. These would be analysed and followed in the next draft. One of the suggestions were that we would need more photographs to fill spaces. P Ruzzi agreed to take more photos from around the area. T Pepperall and A Collett will cooperate on a Gantt chard for the plan.

1. Consultation review.

The Public consultation held at the Parish Hall on 17th March was well attended, even though it snowed most of the day. 40 people signed the attendance sheet, although some people did not sign. It is estimated that about 50 people attended. Thanks to all the helpers on the day. Comments sheets were collected from the post boxes around the Parish, and comments will be reviewed and incorporated into the next draft where possible and relevant.

1. New Draft.

A new Draft has been started by M Sharp, to include the suggestions from the healthcheck and responses. It is quite a big job, and should be ready by the next meeting.

1. Consultation Statement.

The Consultation Statement, at present in preparation, will be delayed while we rewrite the Draft Plan.

1. Basic Conditions Statement.

The Basic Conditions Statement will be revised by P Cole following the healthcheck.

1. Timing.

The schedule produced by T Pepperall will need revising. T Pepperall and A Collett will cooperate on a Gantt plan for the draft.

Next Meeting Tuesday May 1st 2018, JCH at 7.30pm